## Submission Tracker
DATA SUBMISSION TRACKER | [10 empty] | Smartsheet Tip ➜ | Customize the list of possible statuses and priorities to the right so that the Status and Priority columns can use standardized values. |  |  |  |  | STATUS KEY | PRIORITY KEY
[17 empty] | On Hold | Low
|  | PROJECT DETAILS | [9 empty] | DATA ARCHIVING STATUS |  | ADDITIONAL INFO
DATASET | MILESTONE GOAL | WRANGLING STATUS | PRIORITY | ACCESS | ASSAY | PAPER (IF APPLICABLE) | STAGING PORTAL SUBMISSION STATUS | LINK TO SPREADSHEET | PROTOCOLS.IO STATUS | ASSIGNEE | COMMENTS | ARCHIVE | STATUS | TERRA TRANSFER STATUS | PROJECT PAGE UPDATE STATUS https://sspsygene.ucsc.edu/ | IMPORTANT LINKS
ADGC 1 - UCLA
uclaCapstoneBatchA | 2024Q4 | Not Yet Started | Low | Lab | bulk-RNA-seq |  | Not Yet Started |  | Not Yet Started | William | Submit data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (KOLF2.2J) iPSC background lines; fastq)) | NEMO
uclaCapstoneBatchB | 2025Q1 | Not Yet Started | Low | Lab | bulk-RNA-seq |  | Not Yet Started |  | Not Yet Started | William | Submit data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (CIRM) iPSC background lines; fastq)) | NEMO
uclaCapstoneBatchBandC | 2026Q2 | Not Yet Started | Low | Lab | RNA-seq |  | Not Yet Started |  | Not Yet Started | William | Submit data on RNA-seq profiles from Batch B and C ((2 time points x 4 replicates per gene x (90 NPD iPSC lines + 2 controls) x 2 iPSC background lines; fastq)) | NEMO
ADGC 2 - Rutgers & Northshore
rutgersSensorImaging | 2025Q1 | In Progress | Low | Lab | Optical Sensors (imaging) |  | Not Yet Started |  | Not Yet Started | William | Submit imaging data for first set of 200 edited lines (dendritic complexity and synapse quantitation): Partially collected, working with DRACC to submit the data. Note that the analysis will be lagging to cell line creation about 2-3 months (iPSC characterization, iN generation and maturation) | DANDI
rutgersCapstoneScRnaSeq1 | 2025Q1 | Not Yet Started | Low | Lab | sc-RNA-seq |  | Not Yet Started |  | Not Yet Started | William | "Submit scRNA-seq data for first set of 200 edited lines: This has been delayed. We are in the process of processing the first batch of 22 lines with control sequencing. Note that the analysis will be lagging to cell line creation about 2-3 months (iPSC characterization, iN generation and maturation) " | NEMO
rutgersCapstonePatchSeq1 | 2025Q1 | Not Yet Started | Low | Lab | Patch-seq |  | Not Yet Started |  | Not Yet Started | William | "Submit PatchSeq data for first set of 200 edited lines: This needs to be corrected, we will do control in RNAseq first, we are woking with the DRACC to create Cell Browser for visualizing and integrating the data)" | DANDI
rutgersCapstonPatchSeq2 | 2026Q2 | Not Yet Started | Low | Lab | Patch-seq |  | Not Yet Started |  | Not Yet Started | William | Comments | DANDI
rutgersCapstoneOpticalSensors2 | 2026Q2 | Not Yet Started | Low | Lab | Optical Sensors (imaging) |  | Not Yet Started |  | Not Yet Started | William | Submit imaging data for first set of 200 edited lines (synaptic functions using optical sensors): Partially collected, working with DRACC to submit the data. Note that the analysis will be lagging to cell line creation about 2-3 months (iPSC characterization, iN generation and maturation) | BIL
ADGC 3 - Yale
yaleZebrafishBehavior1 | 2024Q2 | Not Yet Started | Low | Lab | quantitative behavioral profiling |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants and stable lines for 10 NPD genes | DANDI
yaleZebrafishBehavior2 | 2024Q2 | Not Yet Started | Low | Lab | quantitative behavioral profiling |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from high-throughput quantitative behavioral profiling for zebrafish mutants of 10 NPD genes. | DANDI
yaleCapstoneMultiOmic | 2024Q3 | Not Yet Started | Low | Lab | multi-omic |  | Not Yet Started |  | Not Yet Started | Brian | Conduct pooled ECCITEseq in hiPSC-NPCs of 10 ASD genes producing >10,000 scRNA-seq profiles | NEMO
yaleMultiOmicCrisprScreen | 2025Q1 | Not Yet Started | Low | Lab | multi-omic |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from multi-omic CRISPR screen of NPD genes in NPCs (fastq). | NEMO
yaleDBiTRNAseq1 | 2025Q1 | Not Yet Started | Low | Lab | DBiT RNA-seq |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from zebrafish transcriptomic and epigenomic analysis of one NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). | NEMO
yaleDBiTATACseq1 | 2025Q1 | Not Yet Started | Low | Lab | DBiT ATAC-seq |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from zebrafish transcriptomic and epigenomic analysis of one NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). | NEMO
yaleMultiOmicScreeniGluts | 2026Q2 | Not Yet Started | Low | Lab | multi-omic |  | Not Yet Started |  | Not Yet Started | Brian | Comments | NEMO
yaleZebrafishBehavior3 | 2026Q2 | Not Yet Started | Low | Lab | quantitative behavioral profiling |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants and stable mutant lines for another 20 NPD genes. | DANDI
yaleMultiOmicScreenHiPSC | 2026Q2 | Not Yet Started | Low | Lab | multi-omic |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from multi-omic CRISPR screen of NPD genes in hiPSCs. | DANDI
yaleDBiTRNAseq2 | 2026Q2 | Not Yet Started | Low | Lab | DBiT RNA-seq |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from zebrafish transcriptomic and epigenomic analysis of another NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). | NEMO
yaleDBiTATACseq2 | 2026Q2 | Not Yet Started | Low | Lab | DBiT ATAC-seq |  | Not Yet Started |  | Not Yet Started | Brian | Submit data from zebrafish transcriptomic and epigenomic analysis of another NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). | NEMO
ADGC 4 – Broad
broadScRNAseq1 | 2025Q1 | Not Yet Started | Low | Lab | sc-RNA-seq |  | Not Yet Started |  | In Progress | Brian | Perform perturb-seq screen of ~150 genes in 4 cell types; submit >100,000 scRNA-seq profiles per cell type (fastq). | NEMO
pilotImageSet | 2025Q1 | Not Yet Started | Low | Lab | images |  | Not Yet Started |  | Not Yet Started | Brian | Comments | BIL
broadScRNAseq2 | 2025Q1 | Not Yet Started | Low | Lab | sc-RNA-seq |  | Not Yet Started |  | Not Yet Started | Brian | Perform census-seq screen of ~40 line village of CIRM lines with and without ASD. Submit RNA-seq profiles from ~10,000 cells | NEMO
broadOpticalEphys1 | 2025Q1 | Not Yet Started | Low | Lab | Optical Electrophysiology |  | Not Yet Started |  | Not Yet Started | Brian | Comments | DANDI
broadCalciumImaging | 2025Q1 | Not Yet Started | Low | Lab | calcium imaging |  | Not Yet Started |  | Not Yet Started | Brian | Perform Perturb-FISH screen of ASD genes in iPS derived astrocytes. Submit ~50 TB of calcium imaging and MERFISH data | DANDI
broadMerfish | 2025Q1 | Not Yet Started | Low | Lab | MERFISH |  | Not Yet Started |  | Not Yet Started | Brian | Perform Perturb-FISH screen of ASD genes in iPS derived astrocytes. Submit ~50 TB of calcium imaging and MERFISH data | DANDI
broadScRNAseq3 | 2025Q1 | Not Yet Started | Low | Lab | sc-RNA-seq |  | Not Yet Started |  | Not Yet Started | Brian | Comments | BIL
broadMorphology1 | 2026Q2 | Not Yet Started | Low | Lab | morphology |  | Not Yet Started |  | Not Yet Started | Brian | Comments | NEMO
broadOpticalEphys2 | 2026Q2 | Not Yet Started | Low | Lab | Optical Electrophysiology |  | Not Yet Started |  | Not Yet Started | Brian | Comments | DANDI
broadMorphologyImaging | 2026Q2 | Not Yet Started | Low | Lab | morphology |  | Not Yet Started |  | Not Yet Started | Brian | Comments | DANDI
broadOpticalEphys3 | 2026Q2 | Not Yet Started | Low | Lab | Optical Electrophysiology |  | Not Yet Started |  | Not Yet Started | Brian | Comments | DANDI
Note on D12: @wisulliv@ucsc.edu @brianlee@ucsc.edu From their milestone doc: "Submit imaging data for first set of 200 edited lines (synaptic functions using optical sensors): Partially collected, working with DRACC to submit the data. Note that the analysis will be lagging to cell line creation about 2-3 months (iPSC characterization, iN generation and maturation)" -Parisa N

## Non-SSPsyGene Wrangling
DATA SUBMISSION TRACKER | [8 empty] | Smartsheet Tip ➜ | STATUS KEY | PRIORITY KEY
[10 empty] | On Hold | Low
PROJECT DETAILS
DATASET | WRANGLING STATUS | PRIORITY | ACCESS | ASSAY | PAPER (IF APPLICABLE) | STAGING PORTAL SUBMISSION STATUS | LINK TO SPREADSHEET | ASSIGNEE | COMMENTS
Aparna/Tom's List
https://www.ncbi.nlm.nih.gov/geo/query/acc.cgi?acc=GSE137101 | Not Yet Started | Low | Public |  | https://www.ncbi.nlm.nih.gov/geo/query/acc.cgi?acc=GSE137101 | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/29867213; PMCID: PMC6028726. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/29867213; PMCID: PMC6028726. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/29539641. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/29539641. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/32923614; PMCID: PMC7450478. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/32923614; PMCID: PMC7450478. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/36509746; PMCID: PMC9744747. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/36509746; PMCID: PMC9744747. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/36318921. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/36318921. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/32999462; PMCID: PMC7957574. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/32999462; PMCID: PMC7957574. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/36007006; PMCID: PMC9614553. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/36007006; PMCID: PMC9614553. | Not Yet Started |  | Parisa
https://www.science.org/doi/10.1126/science.adf1226 | Not Yet Started | Low | Public |  | https://www.science.org/doi/10.1126/science.adf1226 | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/36150908. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/36150908. | Not Yet Started |  | Parisa
Data from iPS villages relevant to the UCLA and Broad groups from their recent publication: "Data from this publication, including read-level whole genome and single-cell RNA sequencing data, are organized at https://app.terra.bio/#workspaces/convergentneuro-mccarroll-anvil/Broad_ConvergentNeuroscience_McCarroll_Nehme_SupplementaryVillageData. Here, we provide instructions for requesting access to scRNA-seq BAM, VCF, WGS BAM, and genomic array files generated from hiPSCs (e.g., iPSC Village-104). Users should visit https://anvilproject.org/data/studies/phs002032 and click “Request Access.” This will send the user to dbGAP (Accession number phs002032). Once granted access by dbGAP, the data can be downloaded from this AnVIL workspace: https://anvil.terra.bio/#workspaces/anvil-datastorage/AnVIL_NIMH_Broad_ConvergentNeuro_McCarroll_Eggan_CIRM_GRU_VillageData." | Not Yet Started | Low | Public |  | Data from iPS villages relevant to the UCLA and Broad groups from their recent publication: "Data from this publication, including read-level whole genome and single-cell RNA sequencing data, are organized at https://app.terra.bio/#workspaces/convergentneuro-mccarroll-anvil/Broad_ConvergentNeuroscience_McCarroll_Nehme_SupplementaryVillageData. Here, we provide instructions for requesting access to scRNA-seq BAM, VCF, WGS BAM, and genomic array files generated from hiPSCs (e.g., iPSC Village-104). Users should visit https://anvilproject.org/data/studies/phs002032 and click “Request Access.” This will send the user to dbGAP (Accession number phs002032). Once granted access by dbGAP, the data can be downloaded from this AnVIL workspace: https://anvil.terra.bio/#workspaces/anvil-datastorage/AnVIL_NIMH_Broad_ConvergentNeuro_McCarroll_Eggan_CIRM_GRU_VillageData." | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/34161264; PMCID: PMC8237684. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/34161264; PMCID: PMC8237684. | Not Yet Started |  | Parisa
https://cells-test.gi.ucsc.edu/?ds=pre-postnatal-cortex | Not Yet Started | Low | Public |  | https://cells-test.gi.ucsc.edu/?ds=pre-postnatal-cortex | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/29217575; PMCID: PMC5991609. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/29217575; PMCID: PMC5991609. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/34616060; PMCID: PMC8494642. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/34616060; PMCID: PMC8494642. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/33723434; PMCID: PMC8012207. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/33723434; PMCID: PMC8012207. | Not Yet Started |  | Parisa
https://www.ebi.ac.uk/biostudies/arrayexpress/studies/E-MTAB-10632 | Not Yet Started | Low | Public |  | https://www.ebi.ac.uk/biostudies/arrayexpress/studies/E-MTAB-10632 | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/34616070; PMCID: PMC8494648. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/34616070; PMCID: PMC8494648. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/31435019; PMCID: PMC6919571. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/31435019; PMCID: PMC6919571. | Not Yet Started |  | Parisa
https://www.ncbi.nlm.nih.gov/geo/query/acc.cgi?acc=GSE205578 | Not Yet Started | Low | Public |  | https://www.ncbi.nlm.nih.gov/geo/query/acc.cgi?acc=GSE205578 | Not Yet Started |  | Parisa
https://www.ncbi.nlm.nih.gov/pmc/articles/PMC8494648/ | Not Yet Started | Low | Public |  | https://www.ncbi.nlm.nih.gov/pmc/articles/PMC8494648/ | Not Yet Started |  | Parisa
https://www.ncbi.nlm.nih.gov/pmc/articles/PMC6677388/ | Not Yet Started | Low | Public |  | https://www.ncbi.nlm.nih.gov/pmc/articles/PMC6677388/ | Not Yet Started |  | Parisa
https://www.ncbi.nlm.nih.gov/pmc/articles/PMC8109149/ | Not Yet Started | Low | Public |  | https://www.ncbi.nlm.nih.gov/pmc/articles/PMC8109149/ | Not Yet Started |  | Parisa
https://www.ncbi.nlm.nih.gov/pmc/articles/PMC10581885/ | Not Yet Started | Low | Public |  | https://www.ncbi.nlm.nih.gov/pmc/articles/PMC10581885/ | Not Yet Started |  | Parisa
https://www.biorxiv.org/content/10.1101/2020.06.29.174383v1 | Not Yet Started | Low | Public |  | https://www.biorxiv.org/content/10.1101/2020.06.29.174383v1 | Not Yet Started |  | Parisa
https://www.ncbi.nlm.nih.gov/pmc/articles/PMC6003669/ | Not Yet Started | Low | Public |  | https://www.ncbi.nlm.nih.gov/pmc/articles/PMC6003669/ | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/31303374; PMCID: PMC6831089. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/31303374; PMCID: PMC6831089. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/34616062; PMCID: PMC8494640. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/34616062; PMCID: PMC8494640. | Not Yet Started |  | Parisa
https://pubmed.ncbi.nlm.nih.gov/37468639. | Not Yet Started | Low | Public |  | https://pubmed.ncbi.nlm.nih.gov/37468639. | Not Yet Started |  | Parisa

## Milestones + Data deadlines
Institute | 2023 Q2 (Apr/May-Jun) | 2023Q3 (Jul-Sep) | 2023 Q4 (Oct-Dec) | 2024 Q1 (Jan-Mar) | 2024 Q2 (Apr/May-Jun) | 2024Q3 (Jul-Sep) | 2024 Q4 (Oct-Dec) | 2025 Q1 (Jan-Mar) | 2025 Q2 - 26 Q2
UCLA |  |  |  | Generate stable clonal iPSC lines for 10 gene mutations in KOLF2.2J (Capstone; Batch A)Generate stable clonal iPSC lines for 10 gene mutations in CIRM line (Capstone; Batch A) | Generate stable clonal iPSC lines for 10 gene mutations in KOLF2.2J (Capstone; Batch A)Generate stable clonal iPSC lines for 10 gene mutations in CIRM line (Capstone; Batch A) Generate stable clonal iPSC lines for additional 25 gene mutations in KOLF2.2J and CIRM (Batch B) QC of Capstone lines to date pending Quantify proliferation rates of NPCs from 10 Capstone iPSC clonal lines Produce data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (KOLF2.2J) iPSC background lines; fastq)) | Generate stable clonal iPSC lines for additional 25 gene mutations in KOLF2.2J and CIRM (Batch B) QC of Capstone lines to date pending Quantify proliferation rates of NPCs from 10 Capstone iPSC clonal lines Produce data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (KOLF2.2J) iPSC background lines; fastq)) Produce bulk RNA-seq profiles ((4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (CIRM line) iPSC background lines; fastq)) Begin villages Begin organoids for first 20 | QC of all generated lines to date pending Generate and QC stable clonal iPSC lines for additional 65 gene mutations in KOLF2.2J and CIRM QC of Capstone lines to date pending Begin StimScope Experiments for 10 capstone lines Produce bulk RNA-seq profiles ((4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (CIRM line) iPSC background lines; fastq)) Submit data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (KOLF2.2J) iPSC background lines; fastq)) Complete villages Prepare samples for RNAseq | QC of all generated lines to date pending Generate and QC stable clonal iPSC lines for additional 65 gene mutations in KOLF2.2J and CIRM Share 20 Batch A gene edited iPSC lines (10 NPD genes x 2 iPSC backgrounds) with other ADGC teams, pending funding to permit expansion and sharing Quantify proliferation rates of NPCs from all iPSC clonal lines from all batches Begin StimScope Experiments for 10 capstone lines Submit data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (CIRM) iPSC background lines; fastq)) Prepare samples for CODEX Perform RNAseq | QC of all generated lines to date pending Generate and QC stable clonal iPSC lines for additional 65 gene mutations in KOLF2.2J and CIRM Share 20 Batch A gene edited iPSC lines (10 NPD genes x 2 iPSC backgrounds) with other ADGC teams, pending funding to permit expansion and sharing Quantify proliferation rates of NPCs from all iPSC clonal lines from all batches Perform codex Begin RNAseq analysis "QC of all generated lines to date pending Generate and QC stable clonal iPSC lines for additional 65 gene mutations in KOLF2.2J and CIRM Share 180 Batch B+C gene edited iPSC lines (90 NPD genes x 2 iPSC backgrounds) with other ADGC teams at end of 25Q1 (pending additional support from NIMH) Quantify proliferation rates of NPCs from all iPSC clonal lines from all batches" "QC of all generated lines to date pending Submit data on RNA-seq profiles from Batch B and C ((2 time points x 4 replicates per gene x (90 NPD iPSC lines + 2 controls) x 2 iPSC background lines; fastq)) Share 180 Batch B+C gene edited iPSC lines (90 NPD genes x 2 iPSC backgrounds) with other ADGC teams at end of 25Q1 (pending additional support from NIMH) Quantify proliferation rates of NPCs from all iPSC clonal lines from all batches Perform StimScope Ephys Experiments for all lines, continuing into early year 5 " Perform StimScope Ephys Experiments for all lines, continuing into early year 6 Share 180 Batch B+C gene edited iPSC lines (90 NPD genes x 2 iPSC backgrounds) with other ADGC teams at end of 25Q1 (pending additional support from NIMH) "Troubleshoot and perform 2nd attempt of difficult KO genes Share 180 Batch B+C gene edited iPSC lines (90 NPD genes x 2 iPSC backgrounds) with other ADGC teams at end of 25Q1 (pending additional support from NIMH) Perform StimScope Ephys Experiments for all lines, continuing into early year 7"
Rutgers, Northshore |  | Create LoF alleles for 9 of 10 capstone genes in 2 capstone iPSC lines (ARID1B, CACNA1G, CHD8, DLL1, GABRA1, KMT2C, SCN2A, SHANK3, and SMARCC2) | Finish creating LoF alleles for capstone genes in 2 capstone iPSC lines, and 4 additional iPSC lines | Bank second set of 200 CRISPR base edited lines (4 backgrounds x 50 lines): We generated 115 lines (22 targeted genes +1 NTC). Note one of the 23 genes targeting not successful "Submit scRNA-seq data for first set of 200 edited lines: This has been delayed. We are in the process of processing the first batch of 22 lines with control sequencing. Note that the analysis will be lagging to cell line creation about 2-3 months (iPSC characterization, iN generation and maturation) " Submit imaging data for first set of 200 edited lines (dendritic complexity and synapse quantitation): Partially collected, working with DRACC to submit the data. Note that the analysis will be lagging to cell line creation about 2-3 months (iPSC characterization, iN generation and maturation) Submit imaging data for first set of 200 edited lines (synaptic functions using optical sensors): Partially collected, working with DRACC to submit the data. Note that the analysis will be lagging to cell line creation about 2-3 months (iPSC characterization, iN generation and maturation) "Submit PatchSeq data for first set of 200 edited lines: This needs to be corrected, we will do control in RNAseq first, we are woking with the DRACC to create Cell Browser for visualizing and integrating the data)" | Production of 72 iPSC lines on average per quarter Production and submitting scRNA-seq data for 72 edited lines produced in the first fiscal year Submit imaging data for 72 edited lines produced in the first fiscal year Submit imaging data forforfor 72 edited lines produced in the first fiscal year submitting Patchseq data for 96 cells | Continued work from Q2 | Continued work from Q2 | Continued work from Q2 | Production of 72 iPSC lines on average per quarter Production and submitting scRNA-seq data for additional 72 edited lines Submit imaging data for additional 72 edited lines Submit imaging data for additional 72 edited lines submitting Patchseq data for 192 cells
Yale | Gene Selection Task Group prioritizes >50 genes. Participate in Launch Meeting (May 11) Volunteers set for each Working / Task Group | Gene Selection Task Group prioritizes >80 genes. Finalize data type definitions with Data Standards Working Group Finalize resources expected to be shared Establish plan for first capstone experiments using 2-3 common workhorse line(s). | Gene Selection Task Group prioritizes 10 Capstone Genes and two control donors. Submit "Assay Implementation Plan" to NIMH by 12/1/2023. Submit revised "Milestones" to NIMH by 12/1/2023. Receive and expand hiPSCs for iCas9 in KOLF2.2 and second control donor Design CRISPRs targeting 10 capstone genes Design CRISPRs targeting 10 genes in parallel with hiPSCs. Obtain available zebrafish lines for the selected NPD genes. | Gene Selection Task Group finalizes 250 NPD genes and 10% negative control genes. Validate gRNA library, prepare lentivirus, validate pool, for 10 capstone ASD genes Generate zebrafish F0 mutants and test available zebrafish lines for 10 NPD genes in parallel with hiPSCs Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants and stable lines for 10 NPD genes Design CRISPRs targeting another 20 genes in parallel with hiPSCs Optimize spatial transcriptomic and epigenomic analysis of larval zebrafish using DBiT-Seq | Generate and validate new dCas9-KRAB-expressing NPC lines from KOLF2.2J and CW20107 hiPSC lines, prepare lentiviral gRNA library targeting 10 ASD genes. Design CRISPRs targeting another 10 NPD genes in parallel with hiPSCs. Submit data from high-throughput quantitative behavioral profiling for zebrafish mutants of 10 NPD genes. Optimize spatial transcriptomic and epigenomic analysis of larval zebrafish using DBiT-Seq. Optimize multi-omic CRISPR screen of NPD genes in hiPSC-NPCs | Conduct pooled ECCITEseq in hiPSC-NPCs of 10 ASD genes producing >10,000 scRNA-seq profiles. If necessary, contrast dCas9 to iCas9 hiPSCs Generate zebrafish F0 mutants for another 10 NPD genes in parallel with hiPSCs. Quantitative behavioral profiling of zebrafish F0 mutants and available mutant lines for another 10 NPD genes. Whole-brain structure and activity mapping of zebrafish F0 mutants and stable lines for 5 NPD genes. Optimize spatial transcriptomic and epigenomic analysis of larval zebrafish using DBiT-Seq. Optimize multi-omic CRISPR screen of NPD genes in hiPSC-NPCs | Conduct pooled ECCITEseq in day 21 iGLUTs of 10 ASD genes producing >10,000 scRNA-seq profiles Sequence and analysis poooled CRISPR screen of 10 NPD genes in hiPSC-NPCs. If necessary, contrast dCas9 to iCas9 hiPSCs Design CRISPRs targeting another 10 NPD genes in parallel with hiPSCs. Generate zebrafish F0 mutants for another 10 NPD genes in parallel with hiPSCs. Generate stable zebrafish mutant lines for 5 NPD genes with the most robust phenotypes. Optimize spatial transcriptomic and epigenomic analysis of larval zebrafish using DBiT-Seq. Optimize multi-omic CRISPR screen of NPD genes in hiPSC-NPCs | Generate stable (targeted?) dCas9-KRAB hiPSCs with dox-inducible ASCL1/DLX2 from KOLF2.2J and CW20107 hiPSCs. Sequence and analysis of pooled CRISPR screen of 10 NPD genes in NPC-iGLUTs. Submit data from multi-omic CRISPR screen of NPD genes in NPCs (fastq). If necessary, contrast dCas9 to iCas9 hiPSCs Quantitative behavioral profiling of zebrafish F0 mutants and available mutant lines for another 10 NPD genes. Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants and stable mutant lines for another 20 NPD genes. Whole-brain structure and activity mapping of zebrafish F0 mutants and stable lines for 5 NPD genes. Generate stable zebrafish mutant lines for 5 NPD genes with the most robust phenotypes. Submit data from zebrafish transcriptomic and epigenomic analysis of one NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). Optimize multi-omic CRISPR screen of NPD genes in hiPSC-NPCs | Conduct pooled ECCITEseq in day 35 iGABA 10 genes, producing >10,000 scRNA-seq profiles. Initiate sequence and analysis of pooled CRISPR screen of 10 NPD genes in iGABAs (to continue in next quarter). Submit data from multi-omic CRISPR screen of NPD genes in iGLUTs (fastq) Generate zebrafish F0 mutants for another 20 NPD genes in parallel with hiPSCs. Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants of another 20 NPD genes. Whole-brain structure and activity mapping of zebrafish F0 mutants and stable lines for another 10 NPD genes. Generate stable zebrafish mutant lines for another 10 NPD genes with the most robust phenotypes. Submit data from zebrafish transcriptomic and epigenomic analysis of another NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). Submit data from multi-omic CRISPR screen of NPD genes in hiPSCs.
Broad | Participate in Launch Meeting (May 11); Volunteers set for each Working / Task Group Finalize data type definitions with Data Standards Working Group; Establish plan for first capstone experiments using 2-3 common workhorse line(s); Gene Selection Task Group prioritizes >200 genes. Submit "Assay Implementation Plan" "Data/Resource Release Plan" and "Milestones" to NIMH by 3/31/2024. Performed pilot morpholgy screen in 20 genes Developed Perturb-FISH for coupled functional and in situ transcriptomic screens | Continued work from Q2 | Continued work from Q2 | Continued work from Q2 | Perform perturb-seq screen of ~150 genes in 4 cell types; submit >100,000 scRNA-seq profiles per cell type (fastq). "Complete validation of initial 20 gene morphological screen. Submit example data set of ~40 TB of images " Develop protocol for scaling up screen size Perform perturb-seq screen of ~150 genes in 4 cell types; submit >100,000 scRNA-seq profiles (fastq) (In parallel to Aim 1) Perform pilot 10 gene electrophysiology screen. Submit ~5 TB of optical electrophysiology data. Perform Perturb-FISH screen of ASD genes in iPS derived astrocytes. Submit ~50 TB of calcium imaging and MERFISH data Perform census-seq screen of ~40 line village of CIRM lines with and without ASD. Submit RNA-seq profiles from ~10,000 cells | Continued work from 2024Q2 | Continued work from 2024Q2 | Continued work from 2024Q2 | "~ 40 TB morphology data ~5 TB optical ephys data ~2 TB morphology imaging ~2 TB optical ephys" "~ 80 TB morphology data ~5 TB optical ephys data ~2 Tb morphology imaging ~2 TB optical ephys"
Institute | 2023 Q2 (Apr/May-Jun) | 2023Q3 (Jul-Sep) | 2023 Q4 (Oct-Dec) | 2024 Q1 (Jan-Mar) | 2024 Q2 (Apr/May-Jun) | 2024Q3 (Jul-Sep) | 2024 Q4 (Oct-Dec) | 2025 Q1 (Jan-Mar) | 2025 Q2 - 26 Q2
UCLA | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | Submit data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (KOLF2.2J) iPSC background lines; fastq) | Submit data from first capstone experiment, producing bulk RNA-seq profiles (4 replicates per gene x (10 NPD iPSC lines + 2 controls) x 1 background (CIRM) iPSC background lines; fastq)) | Submit data on RNA-seq profiles from Batch B and C ((2 time points x 4 replicates per gene x (90 NPD iPSC lines + 2 controls) x 2 iPSC background lines; fastq))
Rutgers, Northshore | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Expected | Submit scRNA-seq data for 72 edited lines produced in the first fiscal year Submit imaging data for 72 edited lines produced in the first fiscal year Submit imaging data forforfor 72 edited lines produced in the first fiscal year submitting Patchseq data for 96 cells | Submit scRNA-seq data for additional 72 edited lines Submit imaging data for additional 72 edited lines Submit imaging data for additional 72 edited lines submitting Patchseq data for 192 cells
Yale | No Data Deadline | No Data Deadline | No Data Deadline | Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants and stable lines for 10 NPD genes | Submit data from high-throughput quantitative behavioral profiling for zebrafish mutants of 10 NPD genes. | No Data Deadline | No Data Deadline | Submit data from multi-omic CRISPR screen of NPD genes in NPCs (fastq). Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants and stable mutant lines for another 20 NPD genes. Submit data from zebrafish transcriptomic and epigenomic analysis of one NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). | Submit data from multi-omic CRISPR screen of NPD genes in iGLUTs (fastq) Submit data from high-throughput quantitative behavioral profiling of zebrafish F0 mutants of another 20 NPD genes. Submit data from zebrafish transcriptomic and epigenomic analysis of another NPD gene, producing 5 DBiT RNA-seq profiles (fastq) and 5 DBiT ATAC-seq profiles (fastq). Submit data from multi-omic CRISPR screen of NPD genes in hiPSCs.
Broad | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | No Data Deadline | Submit >100,000 scRNA-seq profiles per cell type (fastq). Submit example data set of ~40 TB of images " Submit >100,000 scRNA-seq profiles (fastq) (In parallel to Aim 1) Submit ~5 TB of optical electrophysiology data. Submit ~50 TB of calcium imaging and MERFISH data Submit RNA-seq profiles from ~10,000 cells | "~ 40 TB morphology data ~5 TB optical ephys data ~2 TB morphology imaging ~2 TB optical ephys" "~ 80 TB morphology data ~5 TB optical ephys data ~2 Tb morphology imaging ~2 TB optical ephys"